## Sheet1
TEST PLAN DOCUMENTS PROJECT NAME: AMAZON(FRENTEND) Prepared by:sapna sv Date :19 nov 2022
Table of contents Overview-------------------------------------------------------------------- Scope------------------------------------------------------------------------ Inclusion ------------------------------------------------------------- Test environment---------------------------------------------------- Exclusion------------------------------------------------------------- Test strategy---------------------------------------------------------------- Defect reporting procedure----------------------------------------------- Roles/responsibility------------------------------------------------------- Test schedule--------------------------------------------------------------- Test deliverable------------------------------------------------------------ Pricing----------------------------------------------------------------------- Entry and exit criteria----------------------------------------------------- Suspension and resumption criteria--------------------------------- Tools------------------------------------------------------------------------- Risk and mitigation-------------------------------------------------------- Approvals-------------------------------------------------------------------
Overview As a part of the project ,’amazon’ asked sapna sv to test few features of “https:amazon.com/” web appliacation This document serves as test planning documents with details on the scope of the project, test strategy, test schedule and resource requirements,test deliverables and schedule
Scope The scope of the project includes testing the following festures of https://amazon.com/web application Inclusion Hello sign in Language Search Location Cart button Order and return All menu Todays deal Customer service Gift card Registry cell Shop great deals now From our understanding, we believe above functional areas need to be tested. Test environment Windows 10-chrome, firefox ,opera and edge. MAC OS –chrome, firefox, safari browser. Android mobile OS -chrome and opera. I phone mobile OS -chrome and opera. Exclusive All feature which is mention in the ‘inclusion’ except third party application. Test automation.
Test strategy Sapna sv has communicated with ‘amazon’ and has understood that we need to perform all black box testing like (smoke texting,functional testing ,integration testing, system testing,adhoc testing,Globalization testing , performance testing, usability testing, compatibility testing ,web security, exploratory testing ,acceptance testing, regression testing , retesting) for all the functionalities mentioned above scope section. Step1:Creating the test scenarios and test cases. We will write the scenarios, conduct brainstrome meeting prioritize the scenarios bases on customer business workflow,Convert all scenarios into test cases write it in test case templete.We will apply test case design technique while writing functional testing test cases (equivalence partitioning ,boundary value analysis,decision table technique,State transition diagram use case error guessing).Store it in a excel /test case management tool called ALM,jira, etc Review test scenario and test cases from self review ,peer review, management review, inspection ,auditing. Step2:Testing process after getting a build As soon as QA get build we perform smoke testing to check whether the different and important functionality of the application are working.if build is not stable We will reject the build, because QA’s can’t able to continue testing he will block from testing. If build is stable we will continue with the smoke testing. We will do functional testing to make sure that all the components are working fine . We will do integration testing to make data flow between the features are working fine. Once minimum bunch feature are ready and testing server similar to production server setup is available we will do system testing to make Sure that end to end feature are working fine. We will do adhoc testing to make application are stable as per the customer. We will do globalization testing to make sure that appliacation has developed for company standard (date and time format, language, currency format) because amazon has developed for different language. We will do usability testing to make sure that amazon application Is friendly to use / not. We will compatibility testing to make sure that amazon application is working for all OS, browser and hardware as mentioned above test environment. We will do web security testing to make how application is secured from hackers and disaster because it’s a e e-commerce. We will acceptance testing once in demo server for to make sure that all d feature are working fine at one time n using business data without looking into requirement test scenarios and test cases. We will do regression testing/sanity/retesting to make sure that adding deleting modifying fixing the defect is not affect any other old feature. Step 3 :We will follow these two testing for best practice to make our testing is better We will do performance testing to make sure that amazon is working for designed number of users and it will give proper response. We will do exploratory testing for what is unique feature of amazon application we will compare other application which is already in market.
Defect reporting procedure During test execution Anybody from the Testing will configure a server, install a build and start testing. While testing the software any deviation(bug) from expected behavior by application immediately will be reported by giving severity and priority, if not it will be reported as an observation/issues or posted as question. After fixing it again we have to do retesting. If it really fixed close the bug report if not open it again,still process remains constant till the found out bug is fixable,these defect report will be presented in the excel or defect management tolls.
Roles and resposible
Name | Role | Responsibility
Person 1 | Test manager | Test manager review and approve the test plan,Interact with customer, development team, testing team, and management. Test manager will handle the issues and escalations, sign off the release notes, effort estimation, approve the test cases.
Person 2 | Test lead | Test lead will write and review the test plan, allocate work to test engineer, ensure allocated work done on time, consolidate all the reports given by test engineer and send final report to manager, review and approve test cases, prepare traceability matrix.
Person 3 | Test engineer | Test engineer write test scenarios and test cases, review the test cases, test case execution, log to defect tracking tool to lock the defect, knowledge transfern to other team member, brainstorming meeting.
Person 4 | Automation engineer | Automation engineer will be involved in converting test cases Into automation scripts, run the scripts ,update scripts, intall and uninstall the build.
Test schedule
Tasks |  | time duration
Understanding the requirement |  | we have to mention start date and end date for each and every activity.
Identify all the scenarios
Write the test cases
Execute the test cases
Log the defect defects report
Deliverables These are the output documents of testing team this section contains what are going to give to customer by the end of project.
Deliverables |  | Description | Target completion date
Test plan document |  | It is a document which conatins all the testing activities. it consist of overview,scope of the project,test strategy, test schedule,test delieverables,roles and responsibility,pricing,tools risk and mitigation, and approvals
Test scenarios and test cases document |  | this is the high level and detailed level document for to test amazon software, it contains all steps to test a perticular feature.
Traceablity matrix document |  | it is document which ensures that each and every requirement has got atleast one test cases. in this documents contains reverse ,forward and bidirectional traceability matrix.
Test scripts document |  | it is a set of instruction/short program to test any functionality of amazon software application / product. it is a automation approach of amazon software testing.
Test case execution report document |  | it is a document prepared by the test team once after excution gets completed this will give the information of how we are testing all feature.this document shuold preapred by using templets it will vary from company to company.
Defect report document |  | it is a document it consist all defect which is presented in a amazon appliacation which is catch by test engineer for all the feature.
Release notes document |  | it is set document given to customer along with a software which signed by a test manager. it consist of list of pending and open defect ,which platform we are tested and not tested,list of features add,deleted,modified.
Graph and matrics document |  | it is document which is in the form of graph in that we have defect distribution graph,build wise graph,defect trend analysis.metrics is parameter to measure the quality of project from release to release.
Pricing NA
Entry and exit criteria The below are the entry and exit criteria of every phase of software testing life cycle: Requirement analysis Entry criteria: Once the testing team receives the requirement documents or details about the project Exit criteria List of requirement are explored and understood by the testing team doubt are cleared. Test planning Entry criteria Testable requirements derived from the given requirement documents or project details doubt are cleared Exit criteria Test plan document is signed off by the client Test designing Entry criteria Test plan document is signed off by the client. Exit criteria Test plan document is signed off by the client. Test execution Entry criteria Test scenario and test cases documents are signed-off by the client,amazon application is ready in for testing it should be present in the testing server. Exit criteria Test case reports, defect report are ready. Test closure Entry criteria Test case reports defect report are ready Exit criteria Test summary report
Suspension and resumption criteria Based on the client decision, we will suspend and resume the project we will ramp up and ramp down the resources as per client needs. i mean in the testing team they will do some assumption on resources if it is fail suspension and resumption criteria will help.
Tools For test amazon application we should following tools, ALM tool for creating bug tracking. Selenium tool for automation. Google sheet for test scenarios and test case.
Risk and mitigation While testing amazon application testing team will some assumption on resources, technology point, development team, knowledge transfer ,supporting document. Risk :non availability of resources. Mitigation: backup resources planning. Risk :build URL is not working Mitigation: resources will work on other tasks. Risk : less time for testing Mitigation : ramp up the resource based on the client needs dynamically. Risk : development has not yet fof changing lot of requirement changes Mitigation : ask a time to test feature.
Approvals Team will send different type of documents for client approval like below : Test plan Test scenarios Test cases Reports Testing will only continue to the next steps once these approvals are done.